## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Hemanth Srinivas |  | Keyword-based escalation misses complex phrases indicating urgency. | Sprint 2 | Single Developer | Functional | Proposed advanced NLP for synonyms. | 2025-01-26 | Open | Pending advanced NLP implementation.
2 | Hemanth Srinivas |  | Text embedding model clusters unrelated tickets incorrectly. | Sprint 1 | Single Developer | Algorithmic | Improved clustering algorithm. | 2025-01-25 | Closed | Issue resolved with revised logic.
3 | Hemanth Srinivas |  | API integration fails under certain edge case conditions. | Sprint 2 | Single Developer | Integration | Enhanced API error handling. | 2025-01-26 | Open | Requires additional testing.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others